## Slide 1
PLUTO JACKS
NAU ASCE Concrete Canoe 2026
CENE 476 Capstone -- 30% Design Review
February 10, 2026
Team: Trevion | Kayleigh | Amit | Jon | Theo
Advisors: Dr. Lamer PE | Taylor Layland PE
Speaker: Theo
1 / 24
Notes: We're Pluto Jacks, NAU's 2025-2026 ASCE Concrete Canoe team. Five members. Today we present our 30% progress.

## Slide 2
Project Introduction
• Design and build a concrete canoe per ASCE 2026 rules
• National competition: Salt Lake City, University of Utah
• Four event categories: Technical Paper, Oral Presentation, Final Product, Racing
• Team of 5 undergraduate civil engineers at Northern Arizona University
• Faculty Advisor: Dr. Lamer PE
• Graduate Instructor: Taylor Layland PE
[Team Photo Placeholder]
Speaker: Theo
2 / 24
Notes: Purpose: design and build a concrete canoe per ASCE rules. Competing in Salt Lake City at University of Utah. Five-member team from NAU Civil Engineering.

## Slide 3
Project Milestones
Task | Description | Status | Progress
Task 1 | Project Research & Safety | COMPLETE | 100%
Task 2 | Material Testing & Mix Selection | COMPLETE | 100%
Task 3 | Hull Design & Structural Analysis | IN PROGRESS | 60%
Task 4 | Construction & Fabrication | NOT STARTED | 0%
Task 5 | Finishing & Competition Prep | NOT STARTED | 0%
Honest Assessment: We are behind our original schedule.
• Original plan had Task 3 complete by Feb 1 -- revised to Feb 28
• Critical path: Hull design must finalize before mold construction begins
• Mitigation: Increased meeting frequency to 3x/week; parallel-tracking mix optimization
Speaker: Jon
3 / 24
Notes: Task 1-2 complete. Task 3 hull design at 60%. We ARE behind our original schedule but we've adjusted the timeline. Critical path is hull design finalization.

## Slide 4
Task 1.1: Project Research
• ASCE 2026 RFP reviewed cover to cover by all team members
• Key dimensional constraints: maximum 24 ft length, must accommodate 4 paddlers
• Minimum 6 inches of freeboard with 4 paddlers aboard
• Density limitations: concrete must float (< 62.4 PCF)
• Reinforcement: only ASCE-approved fiber or mesh reinforcement
• No metallic reinforcement (rebar, wire mesh) permitted
• Sustainability scoring included for first time in 2026
• Each team member assigned specific rule sections for deep review
Speaker: Kayleigh
4 / 24
Notes: Every team member read the full ASCE 2026 RFP. Key constraints: 6-inch freeboard minimum, density must be below 62.4 PCF (water), only approved non-metallic reinforcement.

## Slide 5
Task 1.2: Sponsorships
• Created personalized outreach videos for each potential sponsor
• Highlighted NAU engineering program and competition visibility
• Sponsors receive logo placement on canoe and in technical paper
Oxendale Auto Group
CONFIRMED
CSEM
CONFIRMED
Additional Sponsors
In Progress
Speaker: Kayleigh
5 / 24
Notes: We created personalized video pitches for sponsors. Oxendale Auto Group and CSEM have confirmed. We're continuing outreach.

## Slide 6
Task 1.3: Lab Safety
• Compiled comprehensive safety binder with all SDS sheets
• Met with lab manager to review emergency procedures
• All team members completed NAU lab safety training
Identified Hazards:
• Alkaline burns from fresh concrete (pH ~12-13)
• Silica dust inhalation (perlite, fly ash)
• Heavy lifting: mold sections weigh 50+ lbs
• Eye protection required during mixing and testing
Required PPE
• Safety glasses / goggles
• Nitrile gloves
• N95 dust masks (perlite mixing)
• Closed-toe shoes
• Long sleeves during pours
Speaker: Kayleigh
6 / 24
Notes: Safety is paramount. Main hazards: alkaline burns from wet concrete, silica dust from perlite and fly ash, heavy lifting. All members trained, safety binder on-site.

## Slide 7
Task 2.1: Material Research
KEY SLIDE -- Aggregate Selection
Specific gravity is the key metric: lower SG = lighter canoe = easier to float
Aggregate | Specific Gravity | Type | Status
Perlite | 0.125 | Volcanic glass | SELECTED
K1 Microspheres | 0.125 | Cenospheres | SELECTED
Poraver | 0.296 | Expanded glass | CANDIDATE
Pumice | 0.641 | Volcanic rock | EVALUATED
Expanded Shale | 1.15 | Lightweight | REJECTED
Natural Sand | 2.65 | Standard | BASELINE
Limestone | 2.70 | Standard | BASELINE
Gravel | 2.75 | Standard | BASELINE
Top 3 aggregates (SG < 1.0) are ultralight -- bottom 4 (SG > 1.0) would make the canoe sink.
Speaker: Theo
7 / 24
Notes: Eight aggregates evaluated. The key is specific gravity. Low SG = lighter canoe = easier to float. Perlite and K1 microspheres at 0.125 are our primary lightweight aggregates.

## Slide 8
Task 2.2: ASTM Testing Standards
ASTM Standard | Test Name | What It Measures | Why It Matters
C39 | Compressive Strength | Max load before crushing | Structural capacity
C143 | Slump Test | Workability / consistency | Thin-shell placement
C138 | Unit Weight | Wet density (PCF) | Must float (< 62.4)
C136 | Sieve Analysis | Particle size distribution | Aggregate grading
C496 | Split Tensile | Indirect tensile strength | Bottom of canoe in tension
C685 | Volumetric Batching | Consistent mix production | Repeatability
All tests performed following ASTM procedures in NAU Concrete Lab.
Speaker: Theo
8 / 24
Notes: Six ASTM test methods guide our material characterization. Each test gives us a specific property we need for the design. C138 density is the most critical -- we need to be below 62.4 PCF.

## Slide 9
ASTM C39: Compressive Strength
• Standard test for compressive strength of cylindrical concrete specimens
• Equipment: Humboldt compression testing machine
• Specimen: 4" diameter x 8" tall cylinders
• Load applied at constant rate until failure
• Failure mode: typically cone or shear fracture pattern
• Results determine if our mix can handle structural loads
• Minimum target: 250 psi at 7 days for thin-shell application
Key Equation
f'c = P / A
(load / cross-section area)
Speaker: Amit
9 / 24
Notes: ASTM C39 is the gold standard for compressive strength. We use 4x8 cylinders in the Humboldt machine. Load until failure and compute f'c = P/A.

## Slide 10
ASTM C143: Slump Test
• Measures workability and consistency of fresh concrete
• Fill cone in 3 layers, rod each layer 25 times, lift cone
• Measure how much the concrete 'slumps' downward
• Target range for canoe: 4-7 inches (fluid enough for thin shell)
• Too low (<3"): won't fill thin mold sections properly
• Too high (>8"): mix may segregate, aggregates settle out
• Thin-shell application demands precise workability control
Speaker: Kayleigh
10 / 24
Notes: Slump test measures workability. For a thin-shell canoe, we need 4-7 inches of slump. Too stiff and we can't fill the mold; too fluid and aggregates segregate.

## Slide 11
ASTM C138: Unit Weight (Density)
CRITICAL MEASUREMENT
THE MOST CRITICAL TEST: Density must be below 62.4 PCF to float.
• Measures wet (fresh) density of concrete in pounds per cubic foot (PCF)
• Fill known-volume container, weigh, compute density = weight / volume
• Water density = 62.4 PCF -- our concrete MUST be lighter
• Target range: 55-65 PCF for lightweight canoe concrete
• Lighter is better, but too light sacrifices strength
• Every aggregate substitution shifts density -- trade-off with strength
THRESHOLD
62.4 PCF
Density of Water
ABOVE = SINKS
BELOW = FLOATS
Speaker: Amit
11 / 24
Notes: Density is our most critical measurement. 62.4 PCF is water's density -- we must be below this. Our target is 55-65 PCF: light enough to float, dense enough for strength.

## Slide 12
ASTM C136: Sieve Analysis
• Determines particle size distribution of aggregates
• Stack of progressively finer sieves shaken mechanically
• Weigh material retained on each sieve
• Well-graded blend: reduces void space between particles
• Fewer voids = less cement paste needed = lower density
• Critical for our ultralight aggregates (perlite, K1, Poraver)
• Sieve sizes: #4, #8, #16, #30, #50, #100, #200, pan
Speaker: Kayleigh
12 / 24
Notes: Sieve analysis gives us particle size distribution. A well-graded blend reduces voids, meaning we need less cement paste. This helps keep density low while maintaining packing efficiency.

## Slide 13
ASTM C496: Split Tensile Strength
• Splitting cylinder test: load cylinder on its side
• Compressive line load induces transverse tension
• Concrete is WEAK in tension -- typically ~10% of compressive strength
• The bottom of the canoe hull is in tension under loading
• This drives our reinforcement strategy (fiber mesh)
• Formula: fct = 2P / (pi * L * D)
Why This Matters:
Canoe bottom is in TENSION under paddler weight. Concrete cracks in tension first.
Speaker: Amit
13 / 24
Notes: Concrete is weak in tension, about 10% of its compressive strength. The bottom of the canoe hull is in tension when paddlers sit on it, so tensile strength and fiber reinforcement are critical.

## Slide 14
ASTM C685: Volumetric Batching
Proof of Work
• Volumetric batching ensures consistent, repeatable mixes
• Each ingredient measured by volume rather than weight for field practicality
• Lab batching procedure documented step-by-step
• Dust masks required during perlite and fly ash handling
• Mix quantities scaled from lab trial (0.1 CY) to production (0.5 CY)
• Graduate Instructor guidance: "Show proof, not just results"
[Lab Mixing Photo]
[Cylinder Casting Photo]
[Testing Photo]
Speaker: Kayleigh
14 / 24
Notes: GI said show proof not just results. This slide shows our actual lab work -- batching, casting cylinders, and testing. Dust masks are essential for perlite handling.

## Slide 15
Task 2.3: Mix Selection Process
3 Precursor Mixes
Literature review & material screening
3 Trial Mixes
Lab-batched & ASTM-tested
Decision Matrix
Weighted criteria scoring
• Systematic approach: research-based precursors -> lab testing -> data-driven selection
• Each mix tested per ASTM C39, C143, C138, C496
• Decision matrix weighted by project priorities (density 30%, strength 25%, workability 20%, cost 15%, sustainability 10%)
Speaker: Theo
15 / 24
Notes: Our process: three precursor mixes from literature, three lab trial mixes, then a weighted decision matrix to select the best. This ensures a data-driven, defensible choice.

## Slide 16
Mix 1: High-Strength Baseline
Property | Result | Target | Verdict
Compressive Strength (7-day) | 3,116 psi | > 250 psi | PASS
Tensile Strength | 385 psi | > 40 psi | PASS
Density | 78.4 PCF | < 62.4 PCF | FAIL
Slump | 1.5" | 4-7" | MARGINAL
DENSITY FAILURE: 78.4 PCF > 62.4 PCF
This mix would SINK. Strong but way too heavy.
Speaker: Theo
16 / 24
Notes: Mix 1 was our high-strength baseline. Excellent compressive strength at 3,116 psi, but density of 78.4 PCF is way above the 62.4 threshold. This canoe would sink.

## Slide 17
Mix 2: Slag Cement Addition
Property | Mix 1 | Mix 2 | Change
Compressive (7-day) | 3,116 psi | ~2,800 psi | Slight decrease
Density | 78.4 PCF | 83.6 PCF | WORSE (+5.2)
Slump | 1.5" | 2.0" | Improved
Additive | -- | Slag cement | Added
• Slag cement improved workability (slump: 1.5" -> 2.0")
• But density got WORSE: 83.6 PCF (even heavier than Mix 1)
• Trade-off lesson: slag helps workability but hurts density
• Key insight: must change AGGREGATES, not just cementitious materials
Speaker: Theo
17 / 24
Notes: Mix 2 added slag cement. Workability improved slightly, but density got WORSE at 83.6 PCF. This taught us that to fix density, we need to change the aggregates, not just the cement.

## Slide 18
Mix 3: Lightweight Breakthrough
MOST IMPORTANT RESULT
Key Changes from Mix 1/2:
• Portland cement cut in HALF: 97 lbs vs 209 lbs
• Added fly ash as supplementary cementitious material
• Increased perlite and K1 microsphere content
• Result: dramatically lower density
Property | Result | Target
Density | 58.6 PCF | < 62.4 PCF
Compressive (7-day) | 307 psi | > 250 psi
Slump | 6.0" | 4-7"
Cost | $1,200/CY | Minimize
IT FLOATS!
58.6 PCF < 62.4 PCF
Density below water threshold
Speaker: Theo
18 / 24
Notes: Our breakthrough. Portland cement cut in half, added fly ash, increased perlite and K1. Density dropped to 58.6 PCF -- below 62.4. This mix FLOATS. Compressive at 307 psi meets our minimum. 6-inch slump is excellent workability.

## Slide 19
Task 2.4: Decision Matrix
• Density weighted 30% -- floating is non-negotiable
• Compressive strength: 25%
• Workability: 20%
• Cost: 15%
• Sustainability: 10%
Mix | Score | Rank
Mix 1: Baseline | 65.20 | 3rd
Mix 2: Slag | 73.53 | 1st
Mix 3: Lightweight | 70.07 | 2nd
Speaker: Theo
19 / 24
Notes: Decision matrix with density weighted at 30% because floating is non-negotiable. Mix 2 scores highest at 73.53, Mix 3 close at 70.07. Both have strengths we want to combine.

## Slide 20
Selected Approach: Optimized Mix 2 + Mix 3 Aggregates
Strategy: Combine Mix 2's cementitious system with Mix 3's aggregate ratios
Mix 2 brings workability and strength from slag cement
Mix 3 brings the lightweight aggregate ratios that achieved 58.6 PCF
Next Steps for Mix Optimization:
• Target: bring density below 62.4 PCF while maintaining strength > 250 psi
• Optimize perlite/K1 ratio for best density-strength trade-off
• Test 28-day strength (expect significant gains over 7-day)
• Scale from 0.1 CY trial batch to 0.5 CY production batch
• Finalize mix design by March 1 for construction start
Speaker: Theo
20 / 24
Notes: Going forward: optimize Mix 2 by incorporating Mix 3's aggregate ratios. The goal is to get the best of both -- workability from slag cement and low density from ultralight aggregates.

## Slide 21
Task 3.1: Hull Design -- Design Criteria & Preliminary Results
CRITICAL SLIDE
ASCE 2026 Requirements
Parameter | Requirement
Freeboard (4-person) | >= 6.0"
Metacentric Height (GM) | >= 6.0"
Safety Factor | >= 2.0 (ACI 318-25 LRFD)
Punching Shear DCR | < 1.0 (ACI 22.6.5.2)
Density | < 62.4 PCF
Candidate Design Results
Parameter | Value | Status
Dimensions | 216" x 36" x 18" | --
Thickness | 0.75" | --
Weight | ~318 lbs | --
Freeboard | 12.82" | PASS
Metacentric Ht | 15.34" | PASS
Safety Factor | 6.39 | PASS
Punch DCR | 0.189 | PASS
Structural analysis per ACI 318-25 LRFD. Cross-checked: Python v2.1 + Excel
Speaker: Trevion
21 / 24
Notes: ASCE requires 6-inch minimum freeboard and adequate stability. Our 216x36x18 design gives 12.82 inches of freeboard -- double the minimum -- and a safety factor of 6.39. Full shear/moment diagrams at 60% review.

## Slide 22
Structural Analysis -- FBD & Section Properties
Parallel axis theorem applied to U-shell cross section
Full structural analysis with shear/moment diagrams at 60% review
Speaker: Trevion
22 / 24
Notes: Free body diagram showing distributed loading, buoyancy, and crew weight. Section properties computed using parallel axis theorem for the U-shell cross section. Full analysis coming at 60% review.

## Slide 23
3D Hull Model -- SolidWorks Dimensions
Speaker: Trevion
23 / 24
Notes: SolidWorks 3D model showing full dimensions of our 216x36x18 inch hull design. The model is used for volume calculations, mold design, and construction drawings.

## Slide 24
References
[1] ACI 318-25, Building Code Requirements for Structural Concrete, ACI, 2025
[2] ASCE 2026 Concrete Canoe Competition Rules & Regulations
[3] ASTM C39/C39M-21, Standard Test Method for Compressive Strength
[4] ASTM C143/C143M-20, Standard Test Method for Slump
[5] ASTM C138/C138M-17a, Standard Test Method for Unit Weight
[6] ASTM C136/C136M-19, Standard Test Method for Sieve Analysis
[7] ASTM C496/C496M-17, Standard Test Method for Splitting Tensile
[8] ASTM C685/C685M-17, Standard Specification for Volumetric Batching
[9] Lewis, E.V., Principles of Naval Architecture, SNAME, 1988
[10] Beer, Johnston, DeWolf, Mechanics of Materials, 8th Ed.
Speaker: Theo
24 / 24
Notes: References for all standards, codes, and textbooks cited in this presentation. ACI 318-25 is the primary structural code. ASCE 2026 RFP governs all competition requirements.